## RACI Matrix
OIT Cyber Lab |  |  |  | Roles and Responsibilities
Responsible, Approves, Supports, Consulted, Informed
| This project covers an overhaul to the OIT cybersecurity lab, adding virtualization, enterprise networking, failover and more to the system to allow for usage of on-prem equipment as a lab environment. |  | ROLES | Professor Gary Lomprey | Admin | Shawn C Ostrander | *Possible* Intel SME | ISC | CIS/CISA | Comments
Deliverable or Task |  | Due Date | Status | Sponsor / Leadership |  | Project Team / Subject Matter Experts
Installation
Plan Install |  | 2025-04-01 | Completed | S |  | R
Install Proxmox |  | 2025-04-01 | Completed | S |  | R
Install Guest OS |  | 2025-04-07 | Completed | S |  | R
Configure Guest OS |  | 2025-04-14 | Completed | S |  | R |  |  | C
Networking
Configure Vlans |  | 2025-04-21 | Completed | S |  | R | C | C | C
Configure network storage |  | 2025-04-21 | In Progress | S |  | R |  |  | C
Configure LAGG |  | 2025-04-21 | Completed | S |  | R | C |  | C
Network Map |  | 2025-05-31 | In Progress | A |  | R | C | C | C
Security
Ensure network configuration is tested |  | 2025-05-14 | Not Started | S |  | R |  |  | C
Ensure Host machines configutation is tested |  | 2025-05-07 | Completed | S |  | R |  |  | C
Ensure Guest machines are tested |  | 2025-05-31 | In Progress | S |  | R |  |  | C
Functionality
Ensure that lab machines are accessable |  | 2025-06-07 | In Progress | S |  | R
Ensure that lab desktops are secure |  | 2025-06-14 | Not Started | S |  | R |  |  | C
Discuss and implement internet policies |  | 2025-06-14 | Not Started | A | C | R |  |  | C
Capstone
Literary review |  | 2025-05-14 | In Progress |  |  | R
Industry review |  | 2025-06-01 | In Progress |  |  | R
Reference gathering and documentation |  | 2025-06-14 | Not Started |  |  | R
Insert new rows (Milestones and Tasks) above as needed
R | Responsible |  | Assigned to complete the task or deliverable. To avoid confusion limit to one entry per task.
A | Approves |  | Has final decision-making authority and accountability for completion. Only 1 per task.
S | Support |  | Provides resources, expertise, tools, access, etc.
C | Consult |  | An adviser, stakeholder, or subject matter expert who is consulted before a decision or action.
I | Informed |  | Must be informed after a decision or action.
Not Started
In Progress
Completed

## Wk 2
Week 2 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week: | This article mostly encapsulates the solution that was used to test RDP connections. A secondary graphical interface was added to the linux guest, xRDP was used to create the RDP connection, and minor internal firewall changes were made to allow RDP traffic on port 3389 https://phoenixnap.com/kb/xrdp-ubuntu There is some consideration to simply use SSH to connect to the guest OS but this is something that would need to be approved by professor Lomprey in a weekly meeting. As such, It will be discussed during the next weekly meeting. While this forum is not a official or reliable resource, It does provide a multitude of options to provide similar functionality to RDP using avariety f different methods. https://askubuntu.com/questions/886313/what-is-the-simplest-way-to-have-remote-gui-access-to-ubuntu-16-04-server-from Relevent risks include unathorized access to VNC or similar services as described in this MITRE ATT&CK article. https://attack.mitre.org/techniques/T1021/005/
Capstone plan started RDP enabled from guest OS from room 255-> room 256. Network changes still needed, and security policies in the works.
2 | List your next steps:
Network changes, and possible restructuring of VLANS so that management traffic and RDP traffic exist on different vlans.
3 | Adjustment to the project plan (if needed):
N/A
4 | Challenges or impediments to progress (how will you manage these?)
xRDP is frustrating to work with due to lack of documentation. I may install windows 11 pro as a guest OS to leverage existing licensing, and work with RDP as Microsoft intends.
5 | Communication with stakeholders:
Communication with stakeholders has been less than optimal this week due to scheduling. While weekly meetings happen due to class, CYB 303, more time needs to be dedicated to ensuring that the project is on track.

## Wk 3
Week 3 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week: | During this week I was also assigned a multi-hour project to work on for Professor Lomprey for his CYB351 class. While this is within scope of this internship, it may slow progress on the lab restoration to some degree. I am hoping that it will not majorly affect time scales, but there is no gaurentees.
Vlan structure modified slightly, and will need more revisions into the future as things change. As of now, work to setup network monitoring systems was undertaken, setting up docker inside of one of the VMs, and setting up graylog to begin performing network monitoring. This step is incomplete, and will require more time and effort to ensure that it is done correctly.
2 | List your next steps:
Finish setting up graylog and other network monitoring devices or services.
3 | Adjustment to the project plan (if needed):
Last week, there was some consideration to simply use SSH instead of RDP. Stakeholders rejected this proposal, and required RDP logins.
4 | Challenges or impediments to progress (how will you manage these?)
Graylog and docker compose were both fighting with the guest OS when attempting to install. I will simply have to spend more time working with the guest OS to ensure that the installation is stable and working before pushing it.
5 | Communication with stakeholders:
Communication with primary stakeholders has been much better this week, with multiple standups occuring throughout the week. Unfortunately this has also involved other work being dumped on my lap.

## Wk 4
Week 4 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week: | Nxlog was brutal this week. For some reason it just would not send anything to Graylog for some time, even though I verified that the port was open with zenmap. I am glad to have a working copy, and hope that duplicating it to a windows server is easy, and will show IIS and other events, similar to WEF.
Graylog was successfully setup using docker-compose. Nxlog was used to forward logs from the windows machine to graylog, allowing monitoring via the GELF format.
2 | List your next steps:
Setup windows server, copy Nxlog config to windows server. Setup accounts/ profiles on proxmox to allow for multi-user remote login. Clean up, then copy VMs, and distribute.
3 | Adjustment to the project plan (if needed):
Network Storage has taken a backseat until now, given the need to make a working copy. If storage becomes an issue, this wil be revisited, as servers are currently not connected to network storage.
4 | Challenges or impediments to progress (how will you manage these?)
Working with open sourced software has been painful at times given the lack of support from vendors. This will be managed by creating a stable, easily repliacable environment, and documenting it thouroughly.
5 | Communication with stakeholders:
Communication with stakeholders has been good this week, but a secondary standup meeting may be in order. This is tentativly planned for Thursday, 4/24, but may change based on scheduling.

## Wk 5
Week 5 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week: | Honestly, If I had known that I would need to be doing this much scripting and input validation, I would have brushed up on my python skills, and maybe my SQL ones too. For some reason Nxlog and graylog just do not want to communicate nicely with one another. I might post a working configuration to the community pages of these platforms once I work it out, because other people should not have to go through this frustration. This type of thing is why support contracts can be helpful.
Windows server is setup, functional and operates IIS reachable over ports 80 and 443. Nxlog forwards msvista logs just fine, but garbles the IIS logs. It appears that it is sending these logs improperly, as both Nxlog as well as graylog are reporting errors. Nxlog is only seeing 15 fields when expecting 17, while graylog is seeing more than 1000 fields.
2 | List your next steps:
Fix field compatability. Rename VMs, and distribute.
3 | Adjustment to the project plan (if needed):
No changes needed beyond described above, but some of these errors may push the project back. As such, more hours may be needed this week, or one of the following.
4 | Challenges or impediments to progress (how will you manage these?)
Nxlog is currently not accepting w3c logs correctly, and graylog is not accepting the fields. As such, I may need to wireshark the packets, and pick them apart to analize what is actually being sent to graylog.
5 | Communication with stakeholders:
Comminication with stakeholders has been present, but given the schedules of both of us, meetings have been brief.

## Wk 6
Week 6 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week:
2 | List your next steps:
3 | Adjustment to the project plan (if needed):
4 | Challenges or impediments to progress (how will you manage these?)
5 | Communication with stakeholders:

## Wk 7
Week 7 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week:
2 | List your next steps:
3 | Adjustment to the project plan (if needed):
4 | Challenges or impediments to progress (how will you manage these?)
5 | Communication with stakeholders:

## Wk 8
Week 8 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week:
2 | List your next steps:
3 | Adjustment to the project plan (if needed):
4 | Challenges or impediments to progress (how will you manage these?)
5 | Communication with stakeholders:

## Wk 9
Week 9 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week:
2 | List your next steps:
3 | Adjustment to the project plan (if needed):
4 | Challenges or impediments to progress (how will you manage these?)
5 | Communication with stakeholders:

## Wk 10
Week 10 Notes
Each week provide updated notes about your capstone by answering/updating using the following prompts: |  | Additional Project/Internships Notes: Use this space to provide evidence of your progress
1 | Work completed during the last week:
2 | List your next steps:
3 | Adjustment to the project plan (if needed):
4 | Challenges or impediments to progress (how will you manage these?)
5 | Communication with stakeholders: